## How to use
Action Planner
Model Anti-Racism Strategy for Local Government: all 75 actions, with filters and columns for council's own implementation plan.
How to use it
Step 1 | On the Actions sheet, use the filter arrows to show the actions for your council type (columns G to I) and the priority you want, for example Essential for rural and remote councils.
Step 2 | Narrow the list further by cost band, "No additional budget", staff effort, pillar or suggested lead team.
Step 3 | Mark each action you want to include with Yes in the Include? column.
Step 4 | Complete the yellow planning columns for each chosen action: responsible team, start and end year, estimated staff days a year, estimated cost a year, and the measure and target.
Step 5 | Check the Summary sheet. Its totals feed the Financial implications section of the Model Council Report and page 2 of the Councillor Briefing.
Step 6 | Copy the chosen actions into Strategy Section 9, keeping the action numbers so the Guideline notes still apply.
Key
Type | Prevent: whole-community actions before racism happens · Target: work with particular groups or settings · Respond: support when racism happens · Recover: helping people and the community recover · All: more than one
Priority (G to I) | Essential: recommended for every council of this type · Recommended: include if capacity allows · Optional: include where it suits local circumstances
Targeted response | Yes means the action can be focused on a particular community when racism against it increases (Strategy Section 3.4).
Excellence option | Yes means a best-practice option for councils choosing to do more.
Cost band | $0 = no additional budget (staff time only) · $ = under $5,000 · $$ = $5,000–$25,000 · $$$ = $25,000–$100,000 · $$$$ = over $100,000 a year. A range means the cost depends on how the action is delivered: $0–$ means no additional budget, or less than $5,000 a year. Bands are indicative: confirm costs locally.
No additional budget | Yes only where the cost band is $0. Actions in the $0–$ band show No, because they may cost up to $5,000 a year. All actions need staff time.
Staff effort | Low: absorbed into normal work, a few days a year, usually by one team · Medium: about one to four weeks a year, or coordination across several teams · High: more than a month a year, a project with external partners, or a dedicated role. Ratings are indicative: confirm them with the managers concerned.
Yellow columns | Fill these in for council's own plan. Every other column is reference information from the model.
Example of a completed row (planning columns only)
Action | 2.1 Include anti-racism information and this strategy in staff and councillor induction
Include? | Yes
Responsible team | People & Culture
Start year / End year | 1 / 1
Est. staff days a year | 3
Est. cost a year ($) | 0
Measure and target | Induction updated by month 6; 100% of new staff complete it
Notes | Combine with the review for Actions 2.2 and 2.3
Published by the Anti-Racism Community Collective · antiracismstrategy.org. Free to use and adapt.

## Actions
No. | Pillar | Action | Type | Targeted response | Excellence option | Metro priority | Regional priority | Rural and remote priority | Cost band | No additional budget | Staff effort | Suggested lead team | Suggested year | Suggested measure | Example councils or source | Include? | Responsible team | Start year | End year | Est. staff days a year | Est. cost a year ($) | Measure and target | Notes
1.1 | 1. Respecting First Nations peoples | Seek advice from [council's Aboriginal and Torres Strait Islander advisory committee / local Aboriginal organisations] on the delivery of this strategy | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Low | Community Development | 1–4 | Advice sought at least [once] a year | Inner West (strategy developed with its Aboriginal and Torres Strait Islander Advisory Committee)
1.2 | 1. Respecting First Nations peoples | Celebrate NAIDOC Week and National Reconciliation Week with local First Nations people and organisations | Prevent |  |  | Essential | Essential | Essential | $–$$ | No | Medium | Community Development / Events | 1–4 | [2] events a year; [80]% of surveyed participants satisfied | Inner West
1.3 | 1. Respecting First Nations peoples | Include First Nations cultures, history and Reconciliation in staff induction | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Low | People & Culture | 1 | Induction updated by [month 6]; [100]% of new staff complete it | Inner West
1.4 | 1. Respecting First Nations peoples | Promote the Call It Out register for reporting racism against First Nations people, and share its annual findings with council's advisory committee | Respond | Yes |  | Essential | Essential | Essential | $0 | Yes | Low | Community Development | 1–4 | Register promoted on council channels [twice] a year; [1] briefing a year to advisory committee | Inner West
1.5 | 1. Respecting First Nations peoples | Include First Nations names and people in council's naming policy priorities | Prevent |  |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Governance / Place | 1–2 | Naming policy updated by end of [Year 2] | Inner West
1.6 | 1. Respecting First Nations peoples | Work with Traditional Owners to protect Aboriginal sites of significance | Prevent |  |  | Recommended | Essential | Essential | $0–$$ | No | Medium | Planning / Heritage | 1–4 | Approach agreed with Traditional Owners by end of [Year 2] | Inner West
1.7 | 1. Respecting First Nations peoples | Support First Nations staff to reduce cultural load and build peer networks | Target |  |  | Recommended | Recommended | Optional | $$ | No | Medium | People & Culture | 1–4 | [75]% of First Nations staff report feeling culturally safe (existing staff survey or check-in) | Inner West ($15,000 p.a.)
1.8 | 1. Respecting First Nations peoples | Create First Nations employment pathways, such as traineeships | Target |  |  | Recommended | Recommended | Recommended | $$$ | No | High | People & Culture | 2–4 | [2] placements a year from [Year 2] | Inner West
1.9 | 1. Respecting First Nations peoples | Encourage local businesses and organisations to develop Reconciliation Action Plans | Prevent |  |  | Recommended | Recommended | Optional | $0 | Yes | Low | Economic Development | 2–4 | [5] local organisations engaged by end of [Year 4] | Inner West (with Reconciliation Australia)
1.10 | 1. Respecting First Nations peoples | Support school events that bring students together to learn about First Nations cultures | Prevent |  |  | Recommended | Recommended | Optional | $–$$ | No | Medium | Community Development | 2–4 | [3] schools participating a year | Darebin (Schools NAIDOC Yarning Conference, cited by AHRC)
1.11 | 1. Respecting First Nations peoples | Create places of recognition and learning, such as memorials or interpretive signage, in partnership with Traditional Owners | Prevent |  | Yes | Optional | Optional | Optional | $$$ | No | High | Place / Community Development | 2–4 | [1] place established by end of [Year 4] | Inner West (Aboriginal Survival Memorials)
2.1 | 2. Leading by example | Include anti-racism information and this strategy in staff and councillor induction | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Low | People & Culture / Governance | 1 | Induction updated by [month 6]; [100]% of new staff and all councillors complete it | Inner West; Waverley
2.2 | 2. Leading by example | Make sure staff know how to raise concerns about racism at work, and that complaints processes deal with racism clearly | Respond |  |  | Essential | Essential | Essential | $0 | Yes | Low | People & Culture | 1 | Process reviewed by [month 6]; communicated to [100]% of staff | Brent Council, UK (Corporate Anti-Racism Action Plan 2024–28)
2.3 | 2. Leading by example | Give frontline staff clear guidance and support for dealing with racist behaviour from customers | Respond | Yes |  | Essential | Essential | Essential | $0 | Yes | Medium | Customer Service / People & Culture | 1 | Guidance issued by [month 6]; [90]% of frontline staff briefed
2.4 | 2. Leading by example | Provide anti-racism training for councillors and staff | Prevent |  |  | Essential | Recommended | Recommended | $$ | No | Medium | People & Culture | 1–2 | [100]% of councillors and [80]% of staff complete training within [24] months | Inner West
2.5 | 2. Leading by example | Invite councillors and senior managers to visit local cultural and faith organisations early in each council term | Prevent | Yes |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Mayor's Office / Community Development | 1 | [3] visits in the first year of each term | Waverley (Mayor and senior staff visits to community institutions each term, generalised)
2.6 | 2. Leading by example | Review HR policies and procedures to strengthen anti-racism and anti-discrimination outcomes | Prevent |  |  | Recommended | Recommended | Optional | $0 | Yes | Medium | People & Culture | 1–2 | Review completed by end of [Year 2] | Inner West
2.7 | 2. Leading by example | Make recruitment more inclusive, for example by advertising through community networks and using diverse interview panels | Target |  |  | Recommended | Recommended | Recommended | $0 | Yes | Medium | People & Culture | 1–4 | [3] recruitment changes implemented by end of [Year 2] | Inner West
2.8 | 2. Leading by example | Encourage suppliers from diverse backgrounds through procurement policies and practices | Prevent |  |  | Recommended | Recommended | Optional | $0 | Yes | Medium | Procurement | 2–3 | Procurement policy updated by end of [Year 3] | Inner West; Darebin (action 3.2.4)
2.9 | 2. Leading by example | Offer mentoring or leadership development for staff from culturally diverse backgrounds | Target |  |  | Recommended | Optional | Optional | $ | No | Medium | People & Culture | 2–4 | [5] participants a year | Inner West
2.10 | 2. Leading by example | Create traineeships or apprenticeships for people from diverse backgrounds | Target |  |  | Recommended | Optional | Optional | $$$ | No | High | People & Culture | 2–4 | [2] placements a year from [Year 2] | Inner West
2.11 | 2. Leading by example | Add a question about experience of racism to council's existing staff survey | Respond |  | Yes | Recommended | Recommended | Optional | $0 | Yes | Low | People & Culture | 1 | Question added by [Year 1] survey; result reported each survey cycle | Inner West (Staff Engagement Survey 2025)
2.12 | 2. Leading by example | Create a dedicated anti-racism officer role | All |  | Yes | Recommended | Optional | Optional | $$$$ | No | High | People & Culture / Community Development | 2 | Role filled by end of [Year 2] | Darebin (the only such position in Australia, per AHRC 2024 mapping report)
3.1 | 3. Fair and welcoming services | Review council's written communications for plain language and accessibility | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Medium | Communications | 1–2 | [20] most-used documents reviewed by end of [Year 2] | Inner West
3.2 | 3. Fair and welcoming services | Make grants criteria and application processes accessible to groups of all backgrounds | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Low | Grants / Community Development | 1 | Criteria reviewed by [month 12]; [25]% of applications from culturally diverse groups | Inner West; Darebin
3.3 | 3. Fair and welcoming services | Make sure venue hire is fair and accessible for community groups of all backgrounds | Prevent | Yes |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Venues / Community Facilities | 1–2 | Hire process reviewed by end of [Year 2] | Darebin (action 2.4.3); Inner West
3.4 | 3. Fair and welcoming services | Make library collections and programs reflect the community's diversity | Prevent |  |  | Essential | Recommended | Recommended | $0 | Yes | Low | Libraries | 1–4 | Collection review by end of [Year 1]; [4] diversity-focused programs a year | Inner West
3.5 | 3. Fair and welcoming services | Improve access to translated information and interpreting | Prevent | Yes |  | Essential | Recommended | Optional | $–$$ | No | Medium | Customer Service / Communications | 1–3 | Key information available in top [5] local languages by end of [Year 3] | Darebin (action 2.1.1: Language Aid, multilingual web content); Inner West
3.6 | 3. Fair and welcoming services | Plan community engagement so the language, place, format and timing work for diverse communities | Prevent |  |  | Recommended | Recommended | Recommended | $0 | Yes | Medium | Engagement | 1–4 | Engagement plans for [100]% of major projects consider language, place, format and timing | Darebin (engagement action 2.1.1)
3.7 | 3. Fair and welcoming services | Make sure sporting ground allocation supports groups of all backgrounds | Prevent |  |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Recreation | 1–2 | Allocation policy reviewed by end of [Year 2] | Inner West (Good Sports and sporting grounds allocation policies)
3.8 | 3. Fair and welcoming services | Consider diverse users when designing parks and open spaces | Prevent |  |  | Recommended | Recommended | Optional | $0 | Yes | Low | Open Space / Place | 1–4 | Diverse users considered in [100]% of new open-space design briefs | Darebin (action 2.4.2)
3.9 | 3. Fair and welcoming services | Promote inclusion and diversity in council's early learning and children's services | Prevent |  |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Children's Services | 1–4 | Inclusion content reviewed annually across [all] services | Inner West
3.10 | 3. Fair and welcoming services | Use images in council communications that reflect First Nations peoples and the community's diversity | Prevent |  |  | Recommended | Optional | Optional | $ | No | Low | Communications | 2 | Image library of [50] images created by end of [Year 2] | Inner West
3.11 | 3. Fair and welcoming services | Check new policies, programs and services for their impact on different communities before they are adopted | Prevent |  | Yes | Recommended | Optional | Optional | $0 | Yes | Medium | Corporate Planning | 2–4 | Impact check applied to [all] new policies from [Year 3] | Darebin (Equity Impact Assessment, Towards Equality framework)
4.1 | 4. Connected communities | Include celebration of local cultures and faiths in council's existing events program | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Low | Events | 1–4 | [3] events a year include cultural content | Inner West
4.2 | 4. Connected communities | Share national anti-racism campaign material, such as the Australian Human Rights Commission's "There's nothing casual about racism", on council channels | Prevent | Yes |  | Essential | Essential | Essential | $0 | Yes | Low | Communications | 1–4 | [4] posts a year | Inner West
4.3 | 4. Connected communities | Mark the International Day for the Elimination of Racial Discrimination (21 March) with community partners | Prevent |  |  | Recommended | Recommended | Recommended | $–$$ | No | Medium | Community Development | 1–4 | [1] event or activity a year | Inner West ($15,000 p.a. grants)
4.4 | 4. Connected communities | Support community-led events that celebrate diverse cultures and faiths, through existing grants | Prevent | Yes |  | Essential | Recommended | Recommended | $0–$$ | No | Low | Grants | 1–4 | [5] community-led events funded a year | Darebin (action 3.1.3); Inner West
4.5 | 4. Connected communities | Work with communities to develop simple resources explaining racism, its effects and how to report it and get support after an experience of racism | Prevent |  |  | Recommended | Recommended | Recommended | $–$$ | No | Medium | Communications / Community Development | 1–2 | Resource published by end of [Year 2] | Inner West; Darebin, Hume and Merri-bek (shared multilingual anti-racism booklet, 2025)
4.6 | 4. Connected communities | Offer bystander ("upstander") training to community groups, sports clubs and businesses | Prevent |  |  | Recommended | Recommended | Optional | $$–$$$ | No | Medium | Community Development | 2–4 | [4] sessions a year; [80]% of participants report greater confidence to respond | Inner West (with Western Sydney University's Challenging Racism Project; $120,000 over two years)
4.7 | 4. Connected communities | Work with local schools to promote evidence-based anti-racism programs | Target |  |  | Recommended | Recommended | Recommended | $0–$ | No | Medium | Community Development / Youth | 2–4 | [3] schools engaged | Inner West
4.8 | 4. Connected communities | Run or support a youth program that builds understanding across cultures and faiths | Target | Yes |  | Recommended | Optional | Optional | $$–$$$ | No | High | Youth Services | 2–4 | [20] young people participating a year | Waverley ("Culture Waves", funded by a state social cohesion grant)
4.9 | 4. Connected communities | Provide or promote business workshops for First Nations and culturally diverse entrepreneurs | Target |  |  | Recommended | Recommended | Optional | $0–$ | No | Medium | Economic Development | 2–4 | [2] workshops a year | Inner West
4.10 | 4. Connected communities | Join a regional anti-racism campaign with neighbouring councils | Prevent |  |  | Recommended | Recommended | Recommended | $ | No | Low | Communications / Community Development | 1–2 | Campaign joined by end of [Year 2] | Greater Hobart councils ("We Stand Together Against Racism", 2025, per council audit)
4.11 | 4. Connected communities | Install anti-racism signage, such as Racism Not Welcome, in consultation with local community groups | Prevent |  |  | Optional | Optional | Optional | $ | No | Low | Community Development | 1–2 | [10] signs installed | City of Sydney; Inner West; Burwood (per council audit)
4.12 | 4. Connected communities | Run a multi-year local anti-racism campaign with community-designed content | Prevent |  | Yes | Recommended | Optional | Optional | $$$ | No | High | Communications | 2–4 | Campaign reach; [3] community-designed pieces a year | Sunshine Coast, Qld ("Shine a Light on Racism", per council audit); Greater Dandenong ("Racism. Get Up. Speak Out.")
4.13 | 4. Connected communities | Run workshops with communities on what racism is, people's rights, and how to report it and get support | Target | Yes |  | Recommended | Recommended | Recommended | $–$$ | No | Medium | Community Development | 2–4 | [4] workshops a year; [70]% of participants know where to report afterwards | Casey and Greater Dandenong roadmap (rec. 2); Whittlesea roadmap (rec. 10)
4.14 | 4. Connected communities | Work with local employers and business groups to prevent racism in local workplaces | Target |  |  | Recommended | Recommended | Optional | $–$$ | No | Medium | Economic Development / Community Development | 2–4 | [10] employers engaged by end of [Year 4] | Casey and Greater Dandenong (employment the most common setting, 58%); Whittlesea (49%)
4.15 | 4. Connected communities | Brief shopping centres, transport operators, health services and security providers on local support services, so their staff can refer people who report racism | Target |  |  | Recommended | Recommended | Optional | $0–$ | No | Low | Community Development | 2–4 | [5] organisations briefed by end of [Year 3] | Whittlesea roadmap (rec. 7, "conduit" stakeholders); shopping centres the most common setting in Wyndham (54%) and Whittlesea (51%)
5.1 | 5. Reporting and responding | Publish clear information on where to report racism and get support (police, human rights bodies, community services) on council's website and at service centres | Respond | Yes |  | Essential | Essential | Essential | $0 | Yes | Low | Communications / Customer Service | 1 | Information published by [month 6]; reviewed annually | Waverley; Hume (anti-racism reporting and support page, per council audit)
5.2 | 5. Reporting and responding | Work with communities to develop a list of local support services and community organisations for referral for support | Respond | Yes |  | Essential | Essential | Essential | $0–$ | No | Medium | Community Development | 1–4 | List updated [annually] | Darebin (action 2.3.1); Waverley (community organisation database)
5.3 | 5. Reporting and responding | Prepare a short plan for how council will respond to a serious racist incident in the community | Respond | Yes |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Community Development / Emergency Management | 1 | Plan in place by end of [Year 1] | Waverley (emergency response plan)
5.4 | 5. Reporting and responding | Work with communities to develop a local racist incident reporting framework (e.g. graffiti, abuse at facilities) and report trends to Council | Respond |  |  | Recommended | Recommended | Recommended | $0–$ | No | Medium | Customer Service / Community Development | 1–4 | Trends reported to Council every [6] months | Waverley (six-monthly reporting)
5.5 | 5. Reporting and responding | Remove racist graffiti from public places quickly and report it to police | Respond | Yes |  | Essential | Essential | Essential | $0 | Yes | Low | City Services | 1–4 | Racist graffiti removed within [24] hours of report | Waverley (reporting through established channels)
5.6 | 5. Reporting and responding | Hold listening sessions with communities affected by a rise in racism | Recover | Yes |  | Recommended | Recommended | Recommended | $0–$ | No | Medium | Community Development | As needed | Session held within [4] weeks of a significant rise | Waverley
5.7 | 5. Reporting and responding | Work with police on safety for community places affected by racism and improving their referrals to other agencies where racism does not reach a criminal threshold | Respond | Yes |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Community Safety | As needed | Safety check requested within [2] weeks. Meeting with local police commands [2] times a year | Waverley (security assessments with police); Whittlesea and Wyndham roadmaps (police referral to support services)
5.8 | 5. Reporting and responding | Provide clear information about approvals and rules for public gatherings in council spaces | Prevent |  |  | Recommended | Recommended | Optional | $0 | Yes | Low | Regulatory Services | 1 | Information published by end of [Year 1] | Waverley
5.9 | 5. Reporting and responding | Add questions on feeling safe and welcome, and on knowing where to report racism, to council's existing community satisfaction survey | Respond |  |  | Essential | Recommended | Recommended | $0–$ | No | Low | Corporate Planning | 1 | Baseline set in [Year 1]; tracked each survey | Woollahra (community satisfaction survey belonging and safety results, used in its Diversity Strategy 2025)
5.10 | 5. Reporting and responding | Establish or join a community-led racism reporting and support network, led by organisations the community already trusts | Respond |  | Yes | Recommended | Optional | Optional | $$$ | No | High | Community Development | 2–4 | Network operating by end of [Year 3] | Wyndham Anti-Racism Support Network (2021); Whittlesea; Casey and Greater Dandenong; Hume, Merri-bek and Darebin
5.11 | 5. Reporting and responding | Promote reporting and support pathways through trusted community organisations and in community languages, not only on council's website | Respond | Yes |  | Essential | Recommended | Recommended | $–$$ | No | Medium | Community Development / Communications | 1–4 | Information promoted through [5] community organisations and in top [5] local languages | All four Victoria University roadmaps: not knowing where to report is the largest single barrier (68% Casey and Greater Dandenong; 71% Wyndham)
5.12 | 5. Reporting and responding | Make sure people can report racism to council anonymously, and promote anonymous options | Respond |  |  | Recommended | Recommended | Recommended | $0–$ | No | Low | Customer Service / Community Development | 1–2 | Anonymous option available and promoted by end of [Year 2] | Casey and Greater Dandenong roadmap (rec. 3)
5.13 | 5. Reporting and responding | Train staff in community-facing services (libraries, neighbourhood houses, customer service) to receive a report of racism, listen, record it and refer the person to support | Respond | Yes |  | Recommended | Recommended | Recommended | $0–$ | No | Medium | Libraries / Community Development / People & Culture | 1–2 | [80]% of staff in named services trained by end of [Year 2] | Wyndham and Whittlesea roadmaps (first-contact organisations; libraries and neighbourhood centres as trusted local venues)
5.14 | 5. Reporting and responding | Publish an annual summary of racism reported locally, with the community organisations involved | Respond |  | Yes | Recommended | Optional | Optional | $0–$ | No | Medium | Community Development | 2–4 | Summary published [annually] from [Year 2] | Whittlesea roadmap (rec. 8); Wyndham support network (coordinating centre role)
5.15 | 5. Reporting and responding | Research local experiences of racism with affected communities, using peer facilitators from those communities | All |  | Yes | Recommended | Optional | Optional | $$$ | No | High | Community Development | 1–2 | Research completed and published by end of [Year 2] | Maribyrnong, Casey and Greater Dandenong, Whittlesea and Wyndham (each with Victoria University)
6.1 | 6. Partnerships and advocacy | Keep a contact list of local cultural, faith and First Nations organisations, and meet them regularly | Prevent | Yes |  | Essential | Essential | Essential | $0 | Yes | Low | Community Development | 1–4 | List maintained; [2] meetings a year | Waverley
6.2 | 6. Partnerships and advocacy | Mayor meets leaders of local cultural and faith communities at the start of each council term | Prevent | Yes |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Mayor's Office | 1 | Meetings held in first [6] months of term | Waverley (generalised)
6.3 | 6. Partnerships and advocacy | Work with neighbouring councils to share resources and coordinate responses | Prevent | Yes |  | Recommended | Recommended | Essential | $0 | Yes | Medium | Community Development | 1–4 | [2] joint activities a year | Waverley (proposed resilience alliance); Darebin, Hume and Merri-bek
6.4 | 6. Partnerships and advocacy | Take part in state or national local government anti-racism networks | Prevent |  |  | Recommended | Recommended | Optional | $0 | Yes | Low | Community Development | 1–4 | Participation maintained | Inner West (engaged with AHRC on the National Framework)
6.5 | 6. Partnerships and advocacy | Advocate to state and federal governments for anti-racism funding and action on local priorities | Prevent |  |  | Recommended | Recommended | Recommended | $0 | Yes | Low | Mayor's Office / Strategy | 1–4 | [1] advocacy submission or letter a year | Inner West
6.6 | 6. Partnerships and advocacy | Seek state and federal grants to fund actions in this strategy | Prevent |  |  | Essential | Essential | Essential | $0 | Yes | Medium | Grants / Community Development | 1–4 | [1] application a year | Waverley (state social cohesion grant)
6.7 | 6. Partnerships and advocacy | Provide free or low-cost venue access to organisations working against racism or discrimination | Target |  |  | Recommended | Recommended | Optional | $0–$ | No | Low | Venues | 1–4 | [5] bookings a year | Inner West
6.8 | 6. Partnerships and advocacy | Work towards the Welcoming Cities Standard | Prevent |  | Yes | Recommended | Recommended | Optional | $–$$ | No | High | Community Development | 2–4 | Accreditation level achieved | Darebin (Welcoming Cities "Excelling" accreditation, 2024)
6.9 | 6. Partnerships and advocacy | Set up a community advisory group to guide and oversee the strategy | All |  | Yes | Recommended | Optional | Optional | $–$$ | No | Medium | Community Development | 1–2 | Group meets [4] times a year | Sunshine Coast (Multicultural Advisory Group, per council audit); Brighton & Hove, UK
6.10 | 6. Partnerships and advocacy | Publish an annual anti-racism scorecard and hold a public progress session | All |  | Yes | Optional | Optional | Optional | $–$$ | No | Medium | Corporate Planning | 2–4 | Scorecard published [annually] | Liverpool City Council, UK (Citywide Anti-Racism Strategy, 2026)
6.11 | 6. Partnerships and advocacy | Pay community members for their time and expertise when they take part in co-design, peer facilitation or advisory work | Target |  |  | Recommended | Recommended | Recommended | $–$$ | No | Low | Community Development | 1–4 | All community contributors offered payment or equivalent recognition | Welcoming Cities and Victoria University guide (payment, certificates and vouchers for community contributors)

## Summary
Summary
Totals update automatically from the Actions sheet.
Your plan
Measure | Value
Actions included | 0
Included actions needing no additional budget ($0) | 0
Included actions with Low staff effort | 0
Included actions with Medium staff effort | 0
Included actions with High staff effort | 0
Estimated staff days a year (included actions) | 0
Estimated full-time equivalent (220 working days a year) | 0
Estimated cost a year (included actions) | 0
The FTE estimate assumes 220 working days a year. Change the 220 in cell B12 to match council's own figure.
Pillar | Included | Of which no additional budget ($0)
1. Respecting First Nations peoples | 0 | 0
2. Leading by example | 0 | 0
3. Fair and welcoming services | 0 | 0
4. Connected communities | 0 | 0
5. Reporting and responding | 0 | 0
6. Partnerships and advocacy | 0 | 0
The full menu
Measure | All actions | Metro | Regional | Rural and remote
Actions in the menu | 75
No additional budget ($0) | 35
Nothing to under $5,000 a year, depending on delivery ($0–$) | 11
Under $5,000 a year ($) | 4
Essential actions |  | 22 | 17 | 18
Essential actions needing no additional budget ($0) |  | 15 | 14 | 15
Essential actions costing nothing to under $5,000 ($0–$) |  | 2 | 1 | 1
Essential actions with High staff effort |  | 0 | 0 | 0